## Slide 1: INTERREG IVC Finance Seminar
Auditors’ Expectations
Petra Geitner, Senior Finance Officer, JTS
Sébastien Cazabonne, Certifying Authority, CDC

## Slide 2: Expectations
Numerous actors to carry out quality checks / audits:
to detect errors and gain assurance of proper use of funds.

## Slide 3: Expectations
Control context
First level control is designed to detect and remove all (or almost) all incorrect expenditure from project claims
Commission view: the maximum acceptable rate of incorrect expenditure after control is around 2%
Recent audits by the Commission and European Court of Auditors have suggested and actual rate of 15%-20%
INTERREG IIIC West: around 7%

## Slide 4: Expectations
What is an irregularity?
« Any infringement of a provision of Community law resulting from an act or omission by an economic operator which has or would have the reffect of prejudicing the general budget of the Communities by charging and unjustified item of expenditure to the Community budget »

## Slide 5: Expectations
Implications for control
Requirements for more written rules, procedures and checklists
better definition of what exactly needs to be checked – increasing control workloads but hopefully providing security for beneficiaires and cotnrollers?
closer supervision of the selection and work of controllers – to ensure independence and that the necessary standards are being achieved
more requirements for quality checking control work particularly through the strengthened role of the Certifying Authority

## Slide 6: Expectations
Main findings:
No evidence of public procurement / tendering
Real cost principle not respected for administration costs (lump sums) and staff costs
Lack of documentation (eg. missing payment proofs)
Publicity requirements not respected

## Slide 7: Expectations
Consequences:
Project has to pay back
funds
Risk of flat rate financial correction which penalizes whole
programme and all MS

## Slide 8: Expectations
Careful reading of
programme documents!
Transparent and extensive
documentation!

## Slide 9: Expectations
Accuracy in establishing and
controlling progress reports.
Doubts about eligibility?
check documents
involve your controller(s) (PP + LP controllers)
Still doubt? Don’t report the costs!

## Slide 10: Further Information
  Operational programme
  Programme manual
  Programme website
    www.interreg4c.eu
  Country specific requirements section
  JTS