## SK
Podrobný harmonogram postupu vydania povolenia k mesiacu 09/2017
Etapy (míľniky) / dĺžka trvania | 2014 |  |  |  | Analógia trvania fáz projektov |  | 2013 | [11 empty] | 2014 | [11 empty] | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021
| 1 | 2 | 3 | 4 |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Študia uskutočniteľnosti | bar: 2013 1 to 2013 4
Zámer EIA | bar: 2014 6 to 2014 10
Rozsah hodnotenia | bar: 2014 11 to 2014 12
Konanie pred podaním žiadosti (1. konanie) |  |  |  |  | SR-HU | SR-PL
Verejné prerokovanie pred predložením žiadosti | bar: 2014 12
Oznámenie projektu (Správa o hodnotení EIA) | bar: 2014 11 to 2015 8
Uznanie oznámenia projektu |  |  |  |  | 16 | 18 | bar: 2015 8
Verejné prerokovania EIA | bar: 2015 9
Koncepcia účasti verejnosti | bar: 2016 5 to 2016 11
Odborný posudok a Záverečné stanovisko EIA | bar: 2015 11 to 2016 1
Rozsah materiálu a kontrolný zoznam | bar: 2016 6 to 2016 11
Podrobný harmonogram postupu vydania povolenia | bar: 2016 5 to 2016 12
FID - realizácia inžinieringu | bar: 2015 7
Osvedčenie na výstavbu - KS | bar: 2015 12 to 2016 2
Osvedčenie na výstavbu - LČ | bar: 2016 4 to 2016 8
Dokumentácia pre územné rozhodnutie - KS | [5 empty] | 4 | bar: 2016 1 to 2016 4
Dokumentácia pre územné rozhodnutie - LČ |  |  |  |  | 2 | 10 | bar: 2016 1 to 2016 11
Správa o zapojení verejnosti | bar: 2016 10 to 2016 12
Zákonné povoľovacie konanie (2. konanie)
Návrh a územné rozhodnutie - KS a LČ | [5 empty] | 4 | bar: 2016 12 to 2017 9
Dokumentácia pre stavebné povolenie - KS | [5 empty] | 13 | bar: 2017 6 to 2017 10
Dokumentácia pre stavebné povolenie - LČ |  |  |  |  | 3 | 9 | bar: 2016 11 to 2017 9
Inžinierska dokumentácia - KS | bar: 2017 8 to 2018 2
Žiadosť a stavebné povolenie - KS | [5 empty] | 8 | [96 empty] | 1 | 1 | 1 | bar: 2017 10 to 2018 4; 2020 1 to 2020 3
Žiadosť a stavebné povolenie - LČ |  |  |  |  | 4 | 7 | bar: 2017 10 to 2018 3
FID - realizácia projektu | bar: 2017 9 to 2017 12
Tender na zhotoviteľa elektrosústrojov - KS | bar: 2015 5 to 2017 10
Výroba elektrosústrojov - KS | bar: 2018 4 to 2019 9
Tender na zhotoviteľov - KS | bar: 2018 5 to 2019 5
Tender na materiály - LČ | bar: 2017 10 to 2018 8
Tender na zhotoviteľov - LČ | bar: 2017 8 to 2018 8
Výstavba, testy a odovzdanie - KS |  |  |  |  | 11 | 25 | bar: 2019 6 to 2020 12
Výstavba, skúšky a odovzdanie - LČ | [5 empty] | 26 | bar: 2018 9 to 2020 11
Skúšobná prevádzka - KS
Skúšobná prevádzka - LČ | bar: 2020 12
povolenia & výstavba
finálne investičné rozhodnutie
[114 empty] | KS | kompresorová stanica (rozšírenie)
[114 empty] | LČ | líniová časť (plynovod)

## EN
Detailed schedule for the permit granting process as of month 09/2017
Milestone / duration | 2014 |  |  |  | Analógia trvania fáz projektov |  | 2013 | [11 empty] | 2014 | [11 empty] | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021
| 1 | 2 | 3 | 4 |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Feasibility Study | bar: 2013 1 to 2013 4
EIA proposal | bar: 2014 6 to 2014 10
Scope of evaluation | bar: 2014 11 to 2014 12
Pre-application procedure (1st procedure) |  |  |  |  | SR-HU | SR-PL
Public consultation before submission of the application file | bar: 2014 12
Notification of project (EIA report) | bar: 2014 11 to 2015 8
Acknowledgement of the notification |  |  |  |  | 16 | 18 | bar: 2015 8
Public consultations EIA | bar: 2015 9
Concept for public participation | bar: 2016 5 to 2016 11
Expertise & Final statement EIA | bar: 2015 11 to 2016 1
Scope of material & checklist | bar: 2016 6 to 2016 11
Detailed schedule for the permit granting process | bar: 2016 5 to 2016 12
FID - engineering | bar: 2015 7
Certificate for construction - CS | bar: 2015 12 to 2016 2
Certificate for construction - PS | bar: 2016 4 to 2016 8
Documentation for zoning decision - CS | [5 empty] | 4 | bar: 2016 1 to 2016 4
Documentation for zoning decision - PS |  |  |  |  | 2 | 10 | bar: 2016 1 to 2016 11
Report of participation of the public | bar: 2016 10 to 2016 12
Statutory procedure (2nd procedure)
Aplication file & zoning decision - (CS&PS) | [5 empty] | 4 | bar: 2016 12 to 2017 9
Documentation for construction permit - CS | [5 empty] | 13 | bar: 2017 6 to 2017 10
Documentation for construction permit - PS |  |  |  |  | 3 | 9 | bar: 2016 11 to 2017 9
Documentation for construction - CS | bar: 2017 8 to 2018 2
Aplication file & construction permit - CS | [5 empty] | 8 | [96 empty] | 1 | 1 | 1 | bar: 2017 10 to 2018 4; 2020 1 to 2020 3
Aplication file & construction permit - PS |  |  |  |  | 4 | 7 | bar: 2017 10 to 2018 3
FID - realization | bar: 2017 9 to 2017 12
Tender for electric units - CS | bar: 2015 5 to 2017 10
Construction of electronic units - CS | bar: 2018 4 to 2019 9
Tender for construction - CS | bar: 2018 5 to 2019 5
Tender for material - PS | bar: 2017 10 to 2018 8
Tender for construction - PS | bar: 2017 8 to 2018 8
Construction, tests & takeover - CS |  |  |  |  | 11 | 25 | bar: 2019 6 to 2020 12
Construction, tests & takeover - PS | [5 empty] | 26 | bar: 2018 9 to 2020 11
Testing operation - CS
Testing operation - PS | bar: 2020 12
permits & construction
final investment decision
[114 empty] | CS | compressor station
[114 empty] | PS | pipeline section